## Dashboard
Qltc Project Tracking System
Design Thinking + Spiral Model ¦ Project Tracker Dashboard (V2)
VERSION |  | OVERALL % COMPLETE |  | BOTTLENECK STAGE | TOPICS TRACKED
2 |  | 17.39% |  | Define | 20
PROGRESS BY PHASE
Stage | Closed | Open | Total | % Complete
Empathise | 20 | 0 | 20 | 100%
Define | 0 | 20 | 20 | 0%
Ideate | 0 | 20 | 20 | 0%
Prototype | 0 | 20 | 20 | 0%
Testing | 0 | 20 | 20 | 0%
Closed (all phases) | 20
Open (all phases) | 80
HOW TO READ THIS DASHBOARD
• Version and Overall % Complete pull live from the Iteration Info block on the main sheet - no manual updates needed.
• Bottleneck Stage highlights whichever phase has the lowest % Complete right now, so you always know where attention is needed.
• The phase table and both charts recalculate automatically as topics move from Open to Closed on the main sheet.

## Project Tracking System V2
Section / Topic | Empathise Version (V2 - Open/Closed) | Details | Responsibility | Target Date | Attachments | Define Version (V2 - Open/Closed) | Details | Responsibility | Target Date | Attachments | Ideate Version (V2 - Open/Closed) | Details | Risk / Assumption | Responsibility | Target Date | Attachments | Prototype Version (V2 - Open/Closed) | Details | Responsibility | Target Date | Attachments | Testing Version (V2 - Open/Closed) | Details | Responsibility | Target Date | Attachments | Iteration Info
A. Client Delivery Projects | [26 empty] | Version | 2
A1. Single Source of Truth | Closed | No single source of truth exists today. SAP B1 Project, Excel To-Do, and the Flutter app are all used inconsistently. Krishna wants something systematic, but keeps falling back to Excel - which has itself multiplied into several inconsistent sheets. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD |  |  |  | Objective | Prove a workable, steady single source of truth for tracking all Qltc projects - client delivery across all 6 verticals AND internal product/innovation initiatives - built on Odoo first, Krishna self-building with Claude as guide
A2. SAP B1 Project & Service Layer - Role Going Forward | Closed | Projects/Sub-Projects and Service Calls/Activities are separate object types in SAP B1 but blur together operationally. SAP B1 is confirmed weak natively for project tracking. SAP B1 stays system of record for financials/service delivery; project tracking moves to a dedicated platform. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD |  |  |  | Owner | Krishna Praveen Rao
A3. Excel Dependency & Retirement | Closed | Primary driver of Excel fallback is speed - typing into a blank sheet beats navigating the app/SAP B1 in the moment. Excel is retired immediately (no parallel transition period) once the new self-update view is live, for whichever verticals/projects are onboarded. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD |  |  |  | Start Date | 2026-08-22
A4. Vertical & Project Scope (All 6 Verticals) | Closed | PARTIAL: confirmed the tracking unit is the project, not the vertical, and that 3 verticals (ERP Implementation, Management System Consulting, Operational Excellence) currently have active projects. NOT YET explored: current project load/activity in the other 3 verticals (Business Development, Project Management, Software Development & Managed Services) - do they have active projects now, or are they dormant/pipeline-only? RESOLVED: Business Development and Project Management verticals are not dormant, but are currently more about marketing/selling Qltc's own services than delivering tracked client projects. Software Development & Managed Services is concretely active: SAP Add-ons (client work), the internal IMS app (B1) and LMS-Moodle (B4) development, and AWS Managed Services for Qltc's own SAP B1 clients - notably, one AWS Managed Services client was recently lost because Qltc could not demonstrate enough added value. This loss is a real, concrete instance of the differentiation/USP problem already named in B5/B6 - worth keeping visible as it reinforces why the product strategy (apps as USP) matters, not just as an abstract argument. V0 SCOPE UPDATE: SAP Add-ons and AWS Managed Services client work are added to V0 pilot scope now, alongside ERP Implementation, Management System Consulting, and Operational Excellence - both live under the Software Development & Managed Services vertical, so V0 effectively covers active client work across 4 verticals from day one, not 3. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD |  |  |  | Target Date
A5. Project Ownership Model | Closed | Status is updated by a named project owner assigned to that specific project - not the vertical lead by default. Owner names to be assigned during rollout, not fixed in advance. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD |  |  |  | Overall % Complete | 0.17391
A6. Update Cadence & Enforcement | Closed | Target cadence is daily updates by project owners, enforced via a 3-day no-update nudge (email) as the backstop rather than a hard daily rule. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
A7. Client Communication / Status Sharing | Closed | Today: occasional email with an Excel attachment - manual, infrequent, disconnected from the tracker. Confirmed out of scope to build for V0; named as a downstream success signal (quick, accurate customer updates pulled from live data). | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
A8. Reporting & At-Risk Definition | Closed | Krishna's view should surface overdue/at-risk projects first. At-risk = past target date OR manually flagged by owner/Krishna. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
A9. Mobile / Desktop / Tablet Access | Closed | Krishna checks status roughly 50/50 desktop vs mobile - solution must work well on both. Satisfied natively by the chosen platform's responsive web + mobile app. UPDATE: with Odoo Enterprise now confirmed (Topic C1), the official native mobile app with offline mode is available (not just the PWA), giving a stronger mobile experience than originally assumed when this topic first closed. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
A10. Security & Access Control | Closed | Roughly 20 people total, all with full visibility - no restricted views/roles needed at this scale. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
B. Product & Innovation Initiatives
B1. IMS Web App (ISO Documentation & Audit) | Closed | Named only so far: a web-based Integrated Management System app focused on ISO documentation and audit. NOT YET explored: current build stage, who's building it, target users (internal team vs sold to clients), timeline pressure, and how it relates to the market-driven USP idea (Topic B5). RESOLVED: team members are building it (not Krishna solo, unlike the tracker itself). Has taken decent shape, meaningful effort invested already - but Krishna is not satisfied on three fronts: features, user-friendliness, and speed of deployment to market. This mirrors the team bottleneck pattern (B7) - effort is going in, but not converting to market-ready output fast enough. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
B2. AI-Integrated CRM in Odoo (Starting with Quotation) | Closed | Named only so far, building on the earlier Odoo-Claude Quote Tracker project. NOT YET explored: current build stage, what 'AI-integrated' means beyond quotation (full CRM scope?), timeline, and relationship to the Odoo-first tracker platform decision (Topic C1) - could this CRM work and the tracker share the same Odoo instance/learnings? RESOLVED: still in the AI-quotation stage (not yet broader CRM). Real milestone reached today (22 Aug 2026) - the first AI-generated quote was actually sent to a client through this system. A lot of work remains, but this is genuine, working progress - not just concept. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
B3. Enhanced HRMS in Odoo | Closed | Named only so far. NOT YET explored: what 'enhanced' means (what's missing from stock Odoo HRMS), current build stage, and timeline. RESOLVED: "enhanced" is benchmarked explicitly against Savior (by STJ Electronics) - a named competitor HRMS product with a stronger feature/reporting set than stock Odoo HRMS. Current stage: getting close to feature/reporting parity with Savior. This gives a concrete target rather than an open-ended "enhance it" brief. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
B4. LMS via Moodle | Closed | Named only so far. NOT YET explored: current build stage, target users (internal training vs a client-facing/market product), and timeline. Also worth clarifying - unlike the other 3 products, this is on Moodle, not Odoo; does that change its priority given the Odoo-first sequencing decision (Topic C1)? RESOLVED: LMS is client-facing today, currently supporting Qltc's other verticals (e.g. training delivery for consulting engagements) - self-hosted on marketplace Moodle freeware/plugins, not deeply customised. Attempts to market it as a standalone product have not worked so far. Krishna wants to go deeper and build substantially on the Moodle platform, having heard of strong results others have achieved with it - this is a genuine build-depth ambition, not just a maintenance item, and is worth its own closer look in Ideate given the stated market failure so far. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
B5. Opportunistic, Market-Driven Product Bets | Closed | Example: a bottling-plant MNC's HIRA & LOTO study request. Krishna's read: the real differentiator (USP) is a user-friendly mobile+desktop app supporting both the one-time study and ongoing sustenance - most competitors won't have this ready. DECISION: tracker logs such an opportunity only once it becomes a committed product bet (Category = Product-Innovation) - sales pipeline stays in Odoo CRM/AI-Quotation (B2). | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
B6. Speed-to-Market & Low-Cost Delivery Pressure | Closed | Traditional order flow is drying up; response speed is now a commercial differentiator, not just capability. This context drives the whole buy-not-build platform pivot (Topic C1) and the push to get products to market quickly and cheaply. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
B7. Execution Capacity - Team Bottleneck | Closed | Original pain: pushing the product agenda to the team is slow, due to skill gaps and competing client-delivery priority. RESOLVED for this initiative: Krishna self-builds V0 with Claude as guide and a few pulled-in resources in a support role - sidesteps the team priority conflict, shifts the constraint to Krishna's own hours. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
C. Platform & Foundation Strategy
C1. Platform Strategy - Odoo vs Zoho, Sequencing | Closed | Researched Odoo Project, Zoho Projects, and Jira against requirements. Odoo has a real manufacturing-depth edge (mature MRP/Shop Floor/Quality/Maintenance) relevant to Qltc's manufacturing specialisation and SAP B1 migration; Zoho's ERP/manufacturing story is new (launched Jan 2026) with documented gaps. Zoho remains attractive for a future retail/service line and is separately viable as a Zoho Consulting Partner offering. DECISION: two-platform strategy long-term (Odoo for manufacturing practice + V0 tracker, Zoho deferred for retail/service), sequenced not parallel - Odoo first. EDITION DECISION: Odoo ENTERPRISE, not Community, chosen from the start. Rationale (debated explicitly): Studio (no-code customisation) directly offsets Krishna's own "little to no hands-on Odoo experience" (Topic C3), lowering build risk for a solo, time-constrained builder. More importantly, the manufacturing depth that justified Odoo over Zoho in the first place - Quality, Maintenance, PLM, Shop Floor - is Enterprise-only; Community's manufacturing is BOM/MO/routing/basic MRP only. Since the long-term goal includes building genuine, sellable Odoo manufacturing-implementation expertise (replacing the SAP B1/R3 practice), Enterprise access is needed for the team to get hands-on with the modules that make that credible to a manufacturing client. Also unlocks the official native mobile app with offline mode (Community/Enterprise both get the PWA; native app + offline is Enterprise-only) and official Odoo support/guaranteed upgrades - relevant risk-reduction for a first-time, solo config effort. Cost acknowledged: roughly 20 users x ~5-40/user/month (~,000-9,600/year) - accepted as worth paying for upfront rather than starting cheap and hitting a wall. | Krishna Praveen Rao / Claude | 2026-08-23 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
C2. Scalable, Extensible Foundation Principle | Closed | Standing design principle: every structural choice should extend cleanly to a new vertical, product, or category without a rebuild. Concrete config: open Vertical field (all 6 available, populated incrementally), Category field (Client Delivery / Product-Innovation), Status + Notes fields - all native custom fields on the chosen platform, no schema engineering needed. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD
C3. Build Ownership & Time Budget | Closed | Krishna will self-build V0 on Odoo, with Claude as guide and a few pulled-in support resources, starting from little/no hands-on Odoo config experience (offset by deep SAP/business-process background). NOT YET defined: how many hours/week Krishna can realistically commit, what a reasonable target date for a working V0 looks like given that, and exactly what the pulled-in support resources will be asked to do. RESOLVED: realistic commitment is 5-10 hrs/week on top of regular work, despite the "burn the midnight oil" intent - worth pacing the plan against this honest number rather than the more aspirational framing. At 5-10 hrs/week, a working Odoo V0 (4 pilot verticals + Status/Notes/Vertical/Category custom fields + at-risk view + 3-day email nudge) is a multi-week effort, not a multi-day one - target date to be set once Ideate defines the exact configuration steps, so the estimate is grounded rather than guessed. | Krishna Praveen Rao | 2026-08-22 |  | Open | TBD |  |  |  | Open | TBD |  |  |  |  | Open | TBD |  |  |  | Open | TBD

## How To Use
How to use this tracker (V2)
This is a restructured V2 of the tracker, rebuilt after the scope expanded significantly during Empathise.
Topics are grouped into 3 sections: A) Client Delivery Projects, B) Product & Innovation Initiatives, C) Platform & Foundation Strategy.
Most Empathise topics already carry a Closed status with the answer already confirmed earlier in this process - these are not being re-asked.
A handful of topics are marked Open in Empathise - these are genuine gaps (the 4 products individually, the other 3 verticals, and the build time budget) that need fresh questions before Empathise can close for V2.
The plan: finish these Open Empathise items first, then move through Define/Ideate/Prototype/Testing for V2, same rhythm as before - but Krishna wants this pace to be deliberate through Empathise/Define/Ideate, and only fast from Prototype onward.